Joint Operational Programme Romania – Republic of Moldova 2014-2020

Annexes

Table of Contents

ANNEX I.  MONITORING AND EVALUATION SYSTEM AND PLAN	3

ANNEX II*. LARGE INFRASTRUCTURE PROJECTS MAIN AND RESERVE LIST	8

ANNEX III.  INFORMATION AND COMMUNICATION STRATEGY AND ANNUAL INFORMATION AND COMMUNICATION PLAN FOR 2016	9

ANNEX IV - REPORT ON THE PROPOSED INDICATORS	32

ANNEX V. REPORT ON STRATEGIC ENVIRONMENTAL ASSESSMENT	58

# Annex I.  Monitoring and Evaluation System and Plan

# Background and Legal Basis

According to the ENI-CBC Implementing Regulation, the programme monitoring and evaluation (M&E) system shall aim to improve the quality of the design and implementation, as well as at assessing and improving its consistency, effectiveness, efficiency and impact. As such, the M&E system will support the preparation, discussion and adoption of key decisions regarding programme strategy and implementation by the JMC. It will also provide important inputs to the programme annual report (including an annual M&E plan) to be sent to the EC by 15 February each year, for the first time in 2016. The technical part of that report shall describe, among other things, the progress achieved in implementing the programme and its priorities. Furthermore, the MA will draw up the programme final report to be approved by the JMC and sent to the EC by 30 September 2024. This should also contain an overview of the achievements of the programme, which will have to be based on M&E system outputs.

# Objectives

The monitoring and evaluation activities will play an important role in the programme implementation cycle. The objective is to put in place a proper risk management by project partners, programme bodies and the EC. In addition, the M&E system will enable learning to take place during project and programme implementation, which will lead to improved performance at both levels. Moreover, the programme and the EC will be better able to safeguard accountability as to the spending of Community and national funds.

The monitoring and evaluation system covers different tools: day to day monitoring, result oriented monitoring reviews and evaluation.

Monitoring is the systematic and continuous data collection against indicators to achieve efficient and effective performance of the project and programme. By day to day monitoring, the activities of the projects or programme are checked whether are on time and on budget as well as delivering as planned. Monitoring allows timely and appropriate measures to be taken if the project or programme is not following the set plan, in order to adapt to changing circumstances and improve the project or programme performance.

The evaluation analyses the full implementation cycle of project or programme and assesses the degree to which results have been achieved and needs met, analysing the reasons for possible underachievement and making recommendations for the rest of the implementation period (in the case of mid-term evaluation) or for similar interventions in the future (in the case of ex-post evaluation).

The result-oriented monitoring also assesses the extent to which planned results and objectives are being achieved. This activity requires data collection on the basis of result indicators (mainly at project level). Corrective action based on the findings of day-to-day monitoring most likely concentrate on activities and the way they are carried out, while ROM may lead to more substantial changes, for example in terms of updating the logical framework, human resources, the budget or carrying out capacity building actions.

In order to meet these objectives, the following activities will be carried out:

- Monitoring at project level

- Monitoring at programme level

- Evaluation

# Monitoring at project level

Monitoring activities shall be carried out at project level, both internally (by the project partners) and externally (by the programme bodies). The aim of the project-level monitoring activities shall be to track progress in project implementation, to take remedial action where necessary as soon as possible, as well as to update action plans.

Objective

According to article 43 of the Implementing Regulation, project applications will have to include a description of monitoring and evaluation arrangements for internal purposes. Projects should describe the way in which the lead partner collects information on the progress of various activities by the other partners, aggregates this information to a regular overview of the state of play of project implementation, and assesses the risks related to possible under-performance in terms of delays, budget overruns or non-achievement of outputs. This assessment should take into account, and be logically connected to, the assumptions formulated in the project logical framework.

Day-to-day monitoring activities by the MA and JTS will consist of a review, in accordance with the applicable procedures, of the progress/interim/final reports, regular contact with the lead partner by e-mail and telephone, meetings, if necessary, and where possible attending key project events, always keeping the other project partners informed as much as possible. Also, specific on-the-spot visits may be carried out to the lead partner/partners premises by MA and/or JTS staff. National authorities may support monitoring visits (both day-to-day and ROM) at the request of the MA. The lead partner is expected to be continuously informed about the developments in project activities carried out by project partners. All monitoring information collected will be stored systematically in the Management Information System (MIS) of the programme.

In addition, there is a need for collecting data to measure programme-level output indicators based on project reports. It will be compulsory for project applications to include the measurement of at least one of the programme output indicators, alongside project-specific output indicators.

The programme will also carry out an internal ROM plan, in the framework of which it will review the performance of projects funded with a focus on the likelihood that results will be achieved and the need for remedial action. The MA may externalise these ROM activities. The following criteria will be used:

- Relevance and design

- Efficiency of implementation

- Effectiveness

- (prospects for) Impact

- (prospects for) Sustainability

ROM reports will also make recommendations to lead partners and partners in order to improve project implementation.

Data collection method

Project applications should, as part of their monitoring arrangements, describe the methodology used for measuring (project level) expected results.

Data collection activities in the framework of ROM may include a review of all relevant project documentation (including project outputs), interviews by telephone/e-mail and, where relevant, face-to-face interviews and/or visits to key project events. The ROM-visits to projects will be planned based on a risk analysis carried out (e.g. on the basis of project amounts or in case previous monitoring visit detected implementation problems). The scale of the visit (only LP or more/all partners) will also be decided upon based on risk analysis, notably the amount allocated to partners.

Data collection frequency

For purposes of project-level monitoring and risk management, the lead partner should check the latest situation in terms of progress in implementation (and assess the corresponding risks) at least once a month. In case of substantial risks, the lead partner should inform the MA immediately. In all other cases, it will report to the MA periodically, in accordance with the grant contract provisions.

Day-to-day monitoring activities by the MA and/or JTS will be carried out on a continuous basis.

Responsible stakeholders

- Lead partner

- Project partners

- JTS

- MA

Project beneficiaries (lead partners) will be responsible for project-level monitoring, including the collection of the relevant information from project partners, the identification and communication of potential bottlenecks (both to other partners and the JTS/MA) and the coordination of solving them. They will also be in charge of submitting project progress reports as well as interim and final reports.

When needed, the national authorities will support the day-to-day monitoring, informing the MA of any actual or threatened bottlenecks in the implementation of project activities in their country and responding to the requests of the MA, according to their competencies and considering the relevant ENI and Programme framework. The MA and JTS will be responsible for day-to-day monitoring and ROM activities at project level.

Output

- Project implementation reports (progress/interim/final)

- Records of day-to-day monitoring activities into programme information system

- ROM reports

# Monitoring at Programme level

The programme has defined its output and result indicators. Monitoring of output indicators will show if the programme is delivering the intended products, whereas monitoring of results indicators will show if the desired wider impact of the programme is taking place.

Objective

Day-to-day monitoring activities at programme level will focus primarily on progress in implementation of the programme in terms of financial and output indicators, as well as its risks and assumptions.

Programme-level ROM will focus on programme performance as well as the likelihood of achievement of target values of the result indicators and will take appropriate actions for improvement. The prospects for programme impact and sustainability will also be addressed.

Data collection method

The basis for data collection will be mainly project reports which represent the main source for measuring the output indicators at programme level, but also for early warnings by lead partners on potential problems in implementation. Nevertheless, national authorities may give early warnings if they anticipate overall difficulties in implementation (e.g. a change of legislation that may create difficulties but normally not on specific projects). Aggregation will be carried out in the framework of the informatic system, where data on progress in terms of launching calls, applications received, the assessment of their quality, contracts signed and project-level on-the-spot visits and audits is also available.

Furthermore, data will be obtained from (summaries of) the evaluation and selection process of applications, contracting, payments (to be extracted from the information system), as well as project-level reports, on-the-spot visits, project level ROM reports and audits.

Programme-level ROM data collection will be based on the aggregation of project level ROM reports.

Data collection frequency

Data on programme output indicators will be collected continuously on the basis of project progress/interim/final reports received.

The result indicators shall be measured once, when the implementation period for most of the projects is finalized, or possibly twice, so to serve as a basis for future programming.

Responsible stakeholders

The primary users of the monitoring and evaluation information will be the programme bodies involved in the management of the programme , as this is a valuable source of information for the day to day management of the programme and reporting on its implementation, communication on its achievements, as well as for the decision making in the JMC. The information can be useful to improve programme, procedures and to better plan monitoring, control and audit activities (on the spot checks, MA controls, provide information to the Audit Authority and the Group of Auditors for their audits on projects, etc.)

The overall responsibility for monitoring and evaluation activities shall rest with the MA and JTS, which will also coordinate the preparation, discussion, JMC approval and submission of the annual report to the EC by 15 February each year. The JTS and MA will also be responsible for uploading data into the KEEP database, based on the information available in the MIS.

The JMC will assess the quality of monitoring and evaluations outputs and discuss their contents, taking these into account when making decisions regarding programme strategy and implementation.

Output

The MA shall submit an annual report approved by the JMC to the EC by 15 February each year. That annual report shall include one technical and one financial part covering the preceding accounting year.

In addition to the annual reports, the programme will provide input to the KEEP database, to which all ENI-CBC programmes will upload information on, amongst others, common output indicators, award procedures, status of beneficiaries and budget allocations per (type of) partner. In addition, KEEP will contain information on the extent to which programmes and projects are achieving their planned results. This will provide the EC with up to date information on the programmes and the possibility to aggregate data across programmes. It will also provide the programmes with the opportunity to use peer programmes as a benchmark for implementation.

The ROM report at programme level will be complemented by ROM reports to be commissioned by the EC at ENI-CBC instrument level. The findings of these reports will be presented to the JMC and they will be discussed as to the need to take corrective action and the related lessons learned.

# Evaluation

According to the ENI Implementing Rules the European Commission can at any moment launch an evaluation or monitoring of the programme or of a part thereof. The results may lead to adjustments in the programme implemented by MA and JMC.

In addition, the programme may commission a programme-specific evaluation (which is likely to take place in 2020), building on the EU-level mid-term evaluation and serving as a basis for future programming. However, the evaluation may also be used as a basis for adjustments of the programmes (reallocation of funds and/or revision of indicators).

Furthermore, according to article 43 of the ENI Implementing Regulation, project applications will have to include a description of monitoring and evaluation arrangements for internal purposes, which may include evaluation activities during or towards the end of their implementation period.

# ANNEX II. LARGE INFRASTRUCTURE PROJECTS MAIN AND RESERVE LIST

| Project title – Main list | Filed of Interest | Thematic Objective | Budget (grant) | Co-financing share | Budget (total) |
| --- | --- | --- | --- | --- | --- |
| Communication Infrastructure | Transport | OT 7 | 5,013,840.00 | 35.72 % | 7,800,000.00 |
| A safer Romanian – Moldavian cross border area infrastructure through the improvement of the operating infrastructure of the Mobile Emergency Service for Resuscitation and Extrication (SMURD) | Emergency Situation | OT 8 | 6,428,000.00 |  | 10,000,000.00 |
| Regional Cooperation for Preventing and Combating Cross-border Crimes between Romania and Republic of Moldova | Internal Affairs | OT 8 | 6,428,000.00 |  | 10,000,000.00 |
| Rehabilitation and modernization of customs offices from the border of Romania and Republic of Moldova (customs offices Albiţa – Leușeni, Sculeni - Sculeni and Giurgiulesti – Giurgiuleşti) | Safety and Security | OT 8 | 6,428,000.00 |  | 10,000,000.00 |
| Project title – Reserve list | Filed of Interest | Thematic Objective | Budget (grant) | Co-financing share | Budget (total) |
| Rehabilitation of the facilities from hydro node - Stânca - Costeşti Phase | Emergency situations | OT 8 | 9,000,000.00 | To be decided by JMC | 10,000,000.00 |

# ANNEX III.  INFORMATION AND COMMUNICATION STRATEGY AND ANNUAL INFORMATION AND COMMUNICATION PLAN FOR 2016

Managing Authority

Ministry of Regional Development and Public Administration

Communication Strategy

Joint Operational Programme Romania – Republic of Moldova 2014-2020

- Introduction

Communication and information dissemination are essential for the successful implementation of the Joint Operational Programme Romania – Republic of Moldova 2014 – 2020. The general public, the potential beneficiaries of the JOP RO-UA 2014-2020, various programme stakeholders (external and internal factors such as the national institutions, European Commission, etc.) must be kept informed throughout the implementation of the Programme.

The ENI CBC Implementing Regulation (IR) stipulates that information on the communication strategy for the whole programme period, and an indicative information and communication plan for the first year should be included in the programme. The guiding principles, the responsible bodies, the visibility rules for information and communication are also specified in other components of the legal framework governing the development and implementation of the ENI CBC in particular that communication is targeted, adequate and is non-discriminatory. These requirements and principles have been taken into account in the preparation of this strategy.

The communication strategy includes the following sections:

- Lessons learned

- General and specific objectives

- Methodological approach

- Identifying and prioritizing target groups

- Communication measures, channels and tools

- Implementing bodies

- Overall timeline and indicative budget

- Monitoring and Evaluation

- Communication plan for the first year

- Lessons learnt

Following the analysis of the Joint Operational Programme Romania – Ukraine – Republic of Moldova 2007-2013 implementation reports, findings, conclusions and recommendations stemming from the result oriented monitoring missions (European Commission),  conclusions of audit/ verification missions undertaken as well as the opinions expressed by various stakeholders during the consultation phase, a range of lessons learnt from 2007-2013 programming period must be taken into account in this respect.

Some of the identified matters and recommendations were already addressed during the implementation of the Programme RO-UA-MD 2007-2013, and they have been also considered in the design of this communication strategy. The main issues to be addressed are:

- Proper consideration to support building up and/or development of effective cross border partnerships since these are the cornerstone on which genuine and successful projects are based on (partner search support).

- More focus on direct communication activities like seminars, training and interactive information events in order to facilitate better understanding of programme requirements;

- More attention to the dissemination of project results, and better visibility of the CBC financed projects in order to capitalise the future project results;

- Improvement of internal communication processes among programme management bodies and with the projects beneficiaries;

- Development of better ITC and on-line tools in order to facilitate communication among potential partners, beneficiaries and stakeholders;

- Capacity building through trainings and information events in order to improve the quality of project proposals;

- Improved consultations with potential beneficiaries before launching the calls for proposals on  guidelines for applicants, manuals and other similar documents;

- The transparency and of communication with the applicants during the evaluation process must be improved;

- The communication plan should include more activities related to project results’ dissemination (e.g. publications, events, dedicated section on Programme website so that to allow the access to models of good practices). Depending on their size and complexity, an inventory of minimum mandatory communication/ promotion/ information activities and/or deliverables might be required from projects in order to ensure adequate visibility.

- General and specific objectives

General objective:

The general objective of the communication strategy is to support achievement of the programme objectives through effective, transparent and relevant communication in order to ensure transparency and increase the awareness of all interested factors as regards the opportunities provided by the programme.

Specific objective no. 1 (addressing programme bodies and the EC):

Ensure a proper implementation of communication procedures and plans among the Programme bodies throughout 2014 – 2020 period as to fulfil all the Programme objectives and results.

Specific objective no. 2 (addressing potential beneficiaries):

Provide and facilitate proper information on the Programme requirements and enhance the capacity of the potential beneficiaries to successfully and effectively implement the projects

Specific objective no. 3 (addressing various stakeholders, donors and the general public):

To increase public awareness and transparency on the actions (to be) performed and the results (to be) achieved by the Programme in the cross border area.

- Methodological approach

Within the overall framework of the general and specific objectives, taking into account the guiding principles given in the legal framework and the lessons learned, the key components of the strategy are to identify for each target group the:

- Purpose of communication;

- Description and prioritisation of the target groups

- Communication tools

- Responsible body

- Indicative timing

The methodology takes into consideration the characteristics of the programme area, and the available programme budget.

The principles essential to the approach proposed include those required by the ENI CBC legal framework and those emerging from the lessons learned. They are:

- Non-discriminatory communication and un-restricted access of all those interested in participating in the calls for proposals launched by the programme;

- Communication with other initiatives being implemented in the programme area and among projects addressing similar problems or working in similar fields

- Efficient communication among programme bodies and the EC leading to better coordination;

- Increased visibility of projects/ programme with focus on results, benefits and their sustainability.

- Identifying and prioritizing target groups

The communication activities will be directed to the target groups identified in the two participating countries, in particular, the eligible regions although it is expected that some communication channels, such as the programme website, will go beyond the programme area.

The target groups to be addressed will be considered according to:

(1) the degree of involvement (supportive or not) in Programme implementation based on the following criteria: substantial involvement, average involvement, minimal involvement;

(2) the impact that the target group might have on achieving the Programme results: high, medium, neutral; (3) usual participatory reaction when addressed: active, apathetic, conjectural.

The groups targeted by the communication strategy, and the purpose of the communication, are outlined below.

Table 1: Communication with programme bodies and the EC

| Nr. | Target group | Prioritization criteria |  |  | Purpose of communication |
| --- | --- | --- | --- | --- | --- |
|  |  | Involvement | Impact | Participatory reaction |  |
| 1. | Programme bodies: Managing Authority (MA), Joint Monitoring Committee (JMC), Audit Authority (AA), National Authorities (NA), Control Contact Points (CCP), Projects Selection Committee (PSC), Joint Technical Secretariat (JTS) and its Branch Offices, | substantial | high | active | Coordinate and efficiently cooperate for the Programme implementation |
| 2. | EC | average | neutral | conjectural | To be kept informed and updated on the progress made by the programme, provides methodological support when required |

Table 2: Communication with potential applicants, beneficiaries and controllers/auditors

| Nr. | Target group | Prioritization criteria |  |  | Purpose of communication |
| --- | --- | --- | --- | --- | --- |
|  |  | Involvement | Impact | Participatory reaction |  |
| 1. | Potential applicants and partners | substantial | high | conjectural | Encourage wide participation at the calls for proposals, facilitate project partnerships and be trained in order to submit good quality applications |
| 2. | Beneficiaries (Lead Beneficiaries and Partners) | substantial | high | active | To be informed about Programme/contract requirements and gain the necessary skills to adequately implement the awarded projects. |
| 3. | Controllers/auditors | substantial | high | conjectural | Perform accurate expenditures verification, in conformity to the grant contract provisions, ENI regulations and the national legislation |

Table 3: Communication with various stakeholders, other donors and the general public

| Nr. | Target group | Prioritization criteria |  |  | Purpose of communication |
| --- | --- | --- | --- | --- | --- |
|  |  | Involvement | Impact | Participatory reaction |  |
| 1. | General public | minimal | neutral | apathetic | Increased awareness about the opportunities and benefits stemming from Programme implementation |
| 2. | Final beneficiaries | average | high | conjectural | To acknowledge and benefit of the results stemming from projects’ implementation |
| 4. | Programme information network | average | medium | conjectural | To further disseminate information related to the Programme within the eligible area |
| 5. | Other EU financing programmes and/ or international donors working in the region* | minimal | neutral | conjectural | To encourage synergies |

*Detailed information regarding other initiatives in the programme area can be found in chapter 3.2.3 of the Programme.

- Communication actions, channels and tools

Communication activities and tools are distributed into three main categories: (1) Promotion, (2) Information and (3) Training.

When deciding for using a particular communication channel the estimated impact is considered, so as the message is passed on with maximum efficiency and at an acceptable cost in line with the Programme budget limitations. Communication activities, channels and tools are chosen based on the specificities of each target group.  Based on the purpose of communication, details of key messages and expected timing will be given in the Annual Communication Plans. A summary table is provided below.

Table 4: Target groups, tools and responsibilities

| Target group | Tools / communication context | Responsible body |
| --- | --- | --- |
| 1.1 Programme bodies | - meetings - written correspondence - promotion and information materials - Programme events - trainings - Programme website | MA/ JTS |
| 1.2 European Commission | - meetings - written correspondence - promotion and information materials - Programme events - Programme website - KEEP database | MA/JTS |
| 2.1 Potential applicants and partners | - media displays - promotion and information materials - guidelines - information and training events - Programme Website / Social Media - Help Desk | MA/ JTS / BO |
| 2.2 Lead Beneficiaries and Partners | - Programme visual identity - media displays - promotion and information materials - guidelines - information and training events - Programme Website / Social Media - Help Desk | MA/ JTS/ BO |
| 2.3 Controllers | - promotion and information materials - guidelines - training events - Programme Website | MA/ JTS / NA |
| 3.1 General public | - Programme identity - media displays - promotion and information materials - information events - Programme Website / Social Media | MA/ JTS / BO |
| 3.2 Programme information network | - promotion and information materials - information events - Programme Website / Social Media | MA/ JTS / BO |
| 3.3 Other EU financing programmes and international donors working in the region | - promotion and information materials - Programme events - Programme website | MA/ JTS |

  - Promotion

    - Programme visual identity

Programme visual identity is essential to individualize the actions funded by the European Union and by the participating countries, and to make visible their results. Visual identity is to be ensured through the programme logo and programme ‘tag’ line i.e. a short phrase that sums up the programme vision. It is recommended to build the new identity on the current one (that of the JOP RO-UA-MD 2007-2013) in order to suggest continuity and commitment.

The visual identity will comply with the Communication and Visibility Manual for EU External Actions and shall incorporate the EU logo.

The visual identity elements will be placed on any communication products, visual and printed materials both produced by programme structures or by projects. The Programme visual identity will be made available to the beneficiaries in accessible formats (including electronic templates) so that to be easy to use.

Requirements for the use of the programme visual identity will be included in the grant contracts provisions. During the calls for proposals period, the applicants might be required to include in their proposals a minimum mandatory set of communication activities to be undertaken at project level, as well as a minimum percentage from the project budget to be spent on this type of operations/ deliverables.

    - Promotional materials

The promotional materials are indispensable for ensuring public awareness and support the Programme recognition and individualization. There tends to be a multiplier effect when being distributed and, if chosen well, they are kept and used by recipients thereby further widening programme visibility on an on-going basis. Useful and eye-catching promotional materials can create a favourable image of the programme making the recipients more receptive to the programme activities.

The promotional materials will be disseminated throughout the Programme implementation period, mainly at various events organized by the Programme and/ or where the Programme is invited.

Project lead beneficiaries and partners are expected to produce their own promotional materials and distribute them during the project events.

    - Media displays

The use of mass media in order to reach a wider audience and promote the programme’s actions and results is an important part of the communication strategy. For both sides of the border, the local and regional media at the county/ raion level must be kept informed in the Programme by providing on regular basis information and specific messages. A tool-kit for working with media might be necessary for a customised and coherent communication, while respecting the visual identity of the Programme.

Objective: To create a set of tools to effectively communicate with the media.

Templates should be used for:

- Press releases

- Press invitations to various Programme events

- Database of media contact (media organisation, editor / reporter etc.)

Mass media will be a major channel to raising public awareness on the programme and to disseminate information on the availability of financial assistance. During project implementation, the focus will be on promoting the results achieved and the benefits brought to communities living across the borders.

Mass-media organisations will be informed of, and invited to, programme events e.g. launching and closing conferences, they will be informed about the launch of calls for proposals and other important programme actions. In each case, programme materials will be distributed and journalists will be directed to the programme website for further information.

Social media may be used to disseminate new programme developments in the informal manner as this is a communication tool already common to other EU programmes used to exchange information and keep up focus and constant interest on their achievements and happenings.

  - Information

    - Programme Website

The programme website www.ro-ua-md.net was one of the key sources of information during implementation of the CBC RO-UA-MD 2007-2013. The web site was recently reorganised, and two new sections concerning the future bilateral programmes at these border have been added. The website played an important role during the programmes preparation period, being the place where the public consultation on various versions of the programme and SEA were launched, and where the legal framework for the future period was made available for potential beneficiaries in order to make them acquainted with the new requirements. For the start-up period of the programme Romania-Republic of Moldova, the website www.ro-ua-md.net will continue to host the Programme Romania-Republic of Moldova section and provide the relevant information for the general public and potential beneficiaries.

A new website will be developed later, following the approval pf the JOP by the European Commission, solely dedicated to the Programme Romania-Republic of Moldova 2014-2020.

The website will be designed to be the main source of information for all the target groups but, in particular, for the potential applicants, the lead beneficiaries and their partners on one hand, and for the general public on the other hand. Information to be uploaded on the Programme website should at least include:

- Information on ENI CBC framework, including the legal provisions and the JOP RO-UA 2014-2020 Programme, other official documents etc.;

- Detailed information on the calls for proposal including the Guidelines for Applicants, information and training support available to potential applicants and partners;

- Frequently asked questions

- Support for finding partners and building partnerships;

- Lists of awarded projects;

- Information and support for projects’ implementation and possibly e-support;

- News, including project news and upcoming events;

- Information/communication on projects events/results achieved by the projects and by the programme;

- Information supporting the activity of programme bodies

- Contact details;

- Guidance, good practices, and links to documents in national languages as necessary etc.;

- Information on events/activities (to be) carried out by the programme bodies;

- Links to the website of the NA in each participating country, other relevant websites, the KEEP database of projects, etc.

The programme website will be promoted during programme events, within all the materials, publications or promotional materials (depending on the space available on the item).

The Joint Technical Secretariat developed in the previous programme ROUAMD 2007-2013 its own web-site to communicate with the general public and Programmes’s beneficiaries and the http://www.brctiași.ro/ is also recognized as a credible and reliable source of information for the Programme that may continue to be used also for this Programme

    - Informative events

Informative events are effective as direct communication ways of bringing information closer to people and communities. Also, they are newsworthy events and are providing opportunities for information to be disseminated to a wider audience via the media.

Informative events should mainly target potential applicants and provide information on the funding opportunities. They are usually accompanied by training events on the application procedures and how to work with the application packages. These types of events also give to those involved in programme implementation the opportunity to underline key information, to share ideas and give insights on what they are doing to achieve the programme objectives.

Specific events to be carried out such as launching and closing conferences, but other events may be placed in the Annual Communication Plans pending on the necessities identified by the programme bodies. Where possible, the programme bodies are encouraged to participate at various events organised at international/ national level by other donors, programmes or by the EC.

    - Programme information Network

To ensure good information and communication flows with the target groups, the MA/JTS/BO will further extend the information network built under the Joint Operational Programme Romania – Ukraine – Republic of Moldova 2007 – 2013. The content and frequency of communication will be further detailed in the Annual Communication Plans. Information will be circulated via this particular network only when relevant.

The Network might include:

- Potential applicants and partners;

- Project lead beneficiaries and partners;

- Other bodies operating in the programme area including ENI CBC programmes, EU cross border programmes and international donors;

- Media contacts.

    - Help Desk

The ‘help desk’ will operate not only during the calls for proposal (respecting the rules governing provision of information during calls), but also during projects implementation, at the headquarters of JTS and Branch Offices (if decided by the Monitoring Committee).

- The Help Desk will be promoted at programme events and on the website, as a tool to assist and support programme potential applicants and beneficiaries.

- Target Groups: Potential applicants and beneficiaries, and their partners

A virtual help desk might be set up, communicating via internet and e-mail with the target groups.

    - Newsletter

The MA/JTS will inform all the target groups on regular basis about the main programme developments via an e-newsletter issued at least once each 4 months. A special template displaying the visual identity elements of the programme will be developed.

The newsletter may include contributions from the participating countries and highlight activities, achievements and results in the respective regions, as well as announcements and relevant information to programme and projects implementation. Distribution will be ensured via the website and the information network.

    - Capitalization of project results

In the context of the communication strategy, capitalisation should be understood as a process of collecting, analysing, transferring and disseminating good practices. It aims at shaping the future actions and strategies both at programme and policy level and to make programme and project achievements more visible.

The capitalisation (results produced by diverse actions) which the programme and its projects have gathered during implementation should be used and transformed into relevant results.

Actions that may use the results of capitalisation:

- Showcasing project results through publications, reports, seminars, events, round tables etc., in strategic topics/ themes identified by the capitalisation working team

- Organising exhibitions showcasing project results in the Programme

- Disseminating press releases on specific topics of particular relevance for capitalisation purposes

- Drafting information briefings for public officials at European, national, and regional level on the added value of projects, feedback on the programme achievements and recommendations for shaping future strategic policy framework for the programme area

  - Training

Training events will be organised with the aim to ensure the necessary competencies at the level of Programme bodies, controllers/auditors as well as potential applicants and beneficiaries. The training events will be organised by the MA/JTS and supported from the TA budget.

The training events will be described in the Annual Communication Plans. Proposed events and target groups include:

- Programme bodies (MA, JTS, NA, CCP, AA & GoAs). For these groups the communication and training should focus on information and development of competencies necessary for programme implementation, including specialised training.

- Potential applicants. During the calls for proposals, the MA/ JTS will organise training sessions in order to enhance capacity to submit valuable, compliant project proposals.

- Lead beneficiaries and partners. After contracting the awarded projects, the MA/JTS will organise training events delivering information which support projects implementation e.g. on contract provisions, reporting procedures etc.

- Controllers/auditors are responsible for performing expenditure verification at project level and, consequently, they need information and training on the grant contract provision, ENI CBC rules, other relevant EU regulations, but also on the main requirements of the task. The NA/CCP of each country, with the support of MA/JTS will organise trainings with the selected auditors and controllers before staring their work. Also, subsequent trainings may be organised when up-dates are necessary.

- Implementing bodies

The ENI CBC IR stipulates that the MA, as well as the lead beneficiaries and partners are responsible for ensuring adequate visibility of the EU contribution to the ENI CBC programmes (Art. 79.1-2).

The Programme’s Communication Strategy will be implemented via Annual Communication Plans. The overall responsibility for the management and implementation of the Annual Communication Plans lies within the MA (IR Art. 26.2f) who will be assisted by the JTS (IR Art. 27.2).

The JMC approves annually the use of TA with the purpose of the communication activity, based on the annual information and communication plan prepared by MA.

- Indicative budget

For the implementation of the Communication Strategy, necessary financial resources will be apportioned from the programme Technical Assistance budget as presented in the table below. If necessary, possible reallocations might be considered during programme implementation when preparing the Annual Communication Plans.

Table 5: Indicative budget by implementation year

| Communication activities/tools | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Promotion | 65,000 | 65,000 | 65,000 | 60,000 | 60,000 | 60,000 | 25,000 | 15,000 | 15,000 | 430,000 |
| Information | 60,000 | 45,000 | 45,000 | 25,000 | 25,000 | 25,000 | 15,000 | 30,000 | 15,000 | 295,000 |
| Training | 30,000 | 30,000 | 30,000 | 14,000 | 14,000 | 12,000 | 12,000 | 12,000 | 5,000 | 159,000 |
| Total | 115,000 | 100,000 | 100,000 | 69,000 | 69,000 | 67,000 | 42,000 | 32,000 | 25,000 | 815,000 |

- Expected results

Expected results of the communication strategy are presented below:

- Potential applicants and partners possess the necessary information and competencies in order to submit valuable, compliant grant applications;

- General public and final beneficiaries are informed of the assistance provided by the programme, participating countries and the EU;

- Programme management bodies and project lead partners and partners receive sufficient training and information to be able to fulfil their roles;

- Lead partners and partners receive sufficient information and support to be able achieve expected results in compliance with the ENI CBC legal framework and national rules;

- Decision makers at national and regional level are supportive towards the Programme.

- Monitoring and Evaluation

The programme communication strategy will be implemented via Annual Information and Communication Plans. The MA, along with the JTS, will be responsible for monitoring the implementation of the Annual Communication Plans. The plans themselves need to be examined and approved by the JMC (IR Art. 24.3).

Information on progress in implementing the Annual Communication Plans will be included in the programme annual report (IR 77.2e) to be submitted to the EC along with a plan for the subsequent year (IR 79.4).

Each annual plan will review implementation of the previous plan. This will involve:

- Analysis of activities planned vs. activities performed, outputs planned vs. outputs achieved;

- Explanations for any modifications to the planning;

- An update on indicators compared to the target indicators;

- Overview of the communication activities and, if necessary, recommendations for adjustments in order to achieve communication targets;

Monitoring of the annual plans will be carried out via output and result indicators given in the table below.

Table 6: Indicators and sources of verification

| Communication activities/tools | Production / Activity indicator | indicator | Source of verification |
| --- | --- | --- | --- |
| Promotion |  |  |  |
| Programme visual identity | Visual elements compliant with EU requirements | - | Sampling of websites and materials produced within the programme |
| Promotional materials | Number of promotional materials produced | Number of materials distributed, by category | Programme annual reports |
| Media displays | Number of journalists invited to events | No of articles | Media monitoring file |
|  | No of press releases issued by the programme and projects |  |  |
| Information |  |  |  |
| Programme Website (maintenance /development) | No of visits per month | - | Website traffic counter |
| Informative events | No of events | No of participants | Event reports |
| Dissemination Network | No of organisations included by the Programme in the network | - | Programme annual reports |
| Help Desk | - | No. of interactions | Help desk register |
| Newsletter | No of newsletter produced | No of recipients | Programme annual reports |
| Training |  |  |  |
| Training sessions | No of training sessions | No of participants | Training reports |

Additional quality indicators will be developed for measuring the satisfaction of the target groups in respect of the communication actions undertaken by the programme.

| Satisfaction (perception) indicator | Source of verification |
| --- | --- |
| Level of satisfaction via evaluation forms filled in after the event (% satisfied or very satisfied) | Event/training reports |
| Level of satisfaction among potential applicants and partners interacting with the help desk (% satisfied or very satisfied) | Feedback system reports (sampling) (On-line, e-mail, etc.) / Event reports |
| Level of satisfaction of programme management bodies expressed via evaluations following training events ((% satisfied or very satisfied) | Feedback system reports (sampling) (On-line, e-mail, etc.) / Event reports |

ANNUAL INFORMATION AND COMMUNICATION PLAN FOR 2016

- Introduction

The communication strategy of the Programme Romania-Republic of Moldova 2014-2020 is implemented via annual information and communication plans (hereafter Annual Communication Plan).

Information on progress in implementing the Annual Communication Plans, the information and publicity measures carried out and the means of communication used will be included in the programme annual report (IR 77.2e) to be submitted to the European Commission (EC) by 15 February along with a plan for the subsequent year (IR 79.4).

This document outlines the Annual Communication Plan for 2016 which follows the Communication Strategy and includes:

- Main communication objectives for 2016

- Target audience for 2016

- Measures, indicative timing, implementing bodies and budget

- Monitoring and Evaluation

- Context and Objectives

The Joint Operational Programme submitted in June 2015 is expected to be adopted by the EC by December 2015. Although preparatory costs, including for the first call for proposals are eligible from the moment of submission of the JOP to the EC, it is anticipated that programme activities in the second half of 2015 will be focused on the set up of management structures and the process for the designation of the Managing Authority (MA). Designation of the MA is expected to be complete in first half of 2016 allowing the launch of the first call for proposals later in the second half of 2016. Therefore the 2016 Annual Communication Plan will focus on the following objectives:

- To ensure a good communication with the programme bodies, as to ensure the proper start-up of the programme.

- To provide and facilitate proper information on the Programme requirements and enhance the capacity of the potential beneficiaries to prepare compliant applications

- To increase public awareness of the new Romania-Republic of Moldova programme 2014-2020.

- Target groups

The information and communication activities will be directed to the target groups identified in the two countries, in particular, in the Programme area, although it is expected that the broader activities, such as the website will reach beyond the eligible regions. Moreover, the programme bodies and the controllers/auditors shall benefit of complete and accurate information concerning the programme, so that to be able to contribute to its proper implementation.

- Communication activities

Proposed activities, target groups, the responsible body, implementing period and indicative budget are outlined in the table bellow:

|  | Activity | Target group | Responsible body | Implement-ing period | Budget |
| --- | --- | --- | --- | --- | --- |
| PROMOTION | Create programme visual identity The visual identity must be created as soon as possible after the adoption of the programme. Some elements of the former programme ROUAMD 2007-2013 may be kept, in order to suggest the continuity and capitalization of the results (e.g. the logo “Common borders. Common solutions”). The new visual identity will be used for the communication tools related to the programme. A new visibility manual for use of programme structures and beneficiaries will be elaborated as well as the design of the main instruments for ensuring programme visibility: roll-up, poster, adds, folders, notebook, pen, etc. | All internal and external target groups | MA/JTS | Q1/Q2 | 10,000 |
|  | Produce and disseminate promotional materials Promotional materials bearing the visual identity elements of the programme will be produced and used or disseminated by MA/JTS during the events related to launch of the programme and of the first call for proposals. The promotional materials produced in 2016 shall include: folders, pens , notebooks , roll ups , posters . | All external target groups; Internal target groups - programme management structures, decision makers in participating countries | MA/JTS | Q2/Q3 | 20,000 |
|  | Social media A new Facebook page will be created in order to disseminate new programme developments in an informal manner. | All internal and external target groups | MA/JTS | Q1 | n/a |
|  | Media displays Press releases will be used to inform the wider public about events such as the launching of the programme, information events, launching of the call for proposals, etc. Additionally, the launching of the call for proposals will be advertised through the media in the eligible area. | All internal and external target groups | MA/JTS |  | 35,000 |
| INFORMATION | Programme website A new programme website will be developed following the approval of the JOP by the European Commission, The website will be designed to be the main source of information for all the target groups but, in particular, for the potential applicants, the lead beneficiaries and their partners on one hand, and for the general public on the other hand. The website will be continuously updated. | All internal and external target groups | MA/JTS | Q1 | 10,000 |
| INFORMATION | Prepare a leaflet on the Programme A leaflet will be produced to give information on the Programme, including the objectives and priorities, eligible regions, expected results and the funds available for each priority. The leaflet will have clear and concise text and attractive graphics. 4500 hard copies will be produced and disseminated during the programme lifetime, but especially in the first year of implementation and before each call for proposals. Electronic copies shall be distributed via the programme website and through the Programme information networks. They will also be sent to the NA for distribution among local stakeholders. | All internal and external target groups | JTS/MA/ NA | Q1/Q2 | 5,000 |
|  | Prepare a leaflet for the first call for proposals Another leaflet will be produced for the first call for proposals. It will give information on the objective of the call, eligible applicants, the types of actions that can be financed, the available amount for the call. It will also include information on the maximum and minimum budget for projects and also the expected duration. Only electronic copies shall be prepared. They will be distributed via the programme website and through the Programme information networks. They will also be sent to the NA for distribution among local stakeholders. | Potential Applicants and partners organisations, EU and other bodies working in the programme area | MA/JTS | Q2/Q3 | n/a |
|  | Update the programme information network will further extend Based on the information network built under the Joint Operational Programme Romania – Ukraine – Republic of Moldova 2007 – 2013, the programme database will be adjusted, so that to include only relevant organisations for the Programme. Updating will also involve adding needed organisations which are not already included such as relevant programme management structures, other bodies operating in the Programme area and relevant national bodies. | Potential beneficiaries, national decision makers, other bodies working in the programme area | JTS/MA/ NA | Q1 | n/a |
| INFORMATION | Programme launching conference The launching conference will be held together with the launching of the first call for proposals. Expected participants will include key decision makers from participating counties, representatives from NA, CCP, other EU programmes, relevant international organisations, potential beneficiaries, including lead partners and partners from the former ENPI programme. The event will give information on the new programme and first call for proposals and will provide a favourable framework for initialising partnerships. | All external target groups, potential beneficiaries, programme management structures, EC, decision makers in participating countries | MA/JTS/ NA | Q3 | 20,000 |
|  | Hold information events in each participating country At least one information event for potential applicants and partners will be held in each participating country as soon as possible after the launch of the call for proposals. These will be one day events held in regions eligible for the programme. They will focus on providing information on the programme, how to participate in the call for proposals and what support is available during the application process. The events are designed to be interactive so to allow sufficient opportunity for discussion and for participants to ask questions. The events will be delivered by the JTS (including BO of JTS) and MA assisted by the NA in each country who will be able to provide information on national rules. | Potential beneficiaries | JTS/MA/ NA | Q3/Q4 | 25,000 |
|  | Establish a Help Desk A virtual ‘help desk’ at programme level, will operate during the first call for proposals (respecting the rules governing provision of information during calls). The Help Desk, established with the JTS and with a dedicated email address, will provide responses to questions of clarification during the calls for proposal. All questions and responses will be published on the programme website. The NA may be requested to support MA with answers related to national rules. The Help Desk will be promoted at programme events, on the programme website and in appropriate publications. | Applicants & partners | JTS/MA | Q3/Q4 | n/a |
| INFORMATION | Prepare a programme newsletter At least one programme newsletter will be produced during 2016. The newsletter will include information about the launch of the new programme and it the opportunities it offers and will also highlight the successes of the current programme. It is expected that contributions to the newsletter, will be made by the participating countries and it will be disseminated via the website and Programme information network. | All internal & external target groups | JTS/MA/ NA | Q2 | n/a |
| TRAINING | Training for programme management structures Training will be conducted for programme management bodies so they are able to fulfil their particular tasks. These events will be organised by the MA/JTS and will coincide with other programme events where possible. | MA, NA, JTS, CCP, AA, GoA | MA/JTS | Q1-Q2 | 5,000 |
|  | Trainings for potential beneficiaries | Potential beneficiaries | MA/JTS | Q3 | 25,000 |

# 2014-2020 Romania - Republic of Moldova CBC Programme

# Annex IV - Report on the proposed indicators

# Table of contents

Introduction	34

Presentation of the proposed indicators	35

Priority 1.1 – Institutional cooperation in the educational field for increasing access to education and quality of education	35

Summary of indicators	35

Methodological details on proposed indicators	36

Priority 1.2 – Promotion and support for research and innovation	40

Summary of indicators	40

Methodological details on proposed indicators	40

Priority 2.1 – Preservation and promotion of the cultural and historical heritage	41

Summary of indicators	42

Methodological details on proposed indicators	42

Priority 3.1 –Development of cross border transport infrastructure and ICT Infrastructure	44

Summary of indicators	44

Methodological details on proposed indicators	45

Priority 4.1 - Support to the development of health services and access to health	49

Summary of indicators	49

Methodological details on proposed indicators	49

Priority 4.2 – Support to joint activities for the prevention of natural and man-made disasters as well as joint action during emergency situations	52

Summary of indicators	52

Methodological details on proposed indicators	52

Priority 4.3 Prevention and fight against organized crime and police cooperation	54

Summary of indicators	54

Methodological details on proposed indicators	55

# Introduction

The document provides details and methodological explanations on the system of indicators proposed for the programme.

The objective of this report is to support the programming process and to provide the Joint Managing Authority, the Joint Programming Committee as well as the relevant national authorities the indicators for the 2014-2020 Romania-Republic of Moldova CBC Programme together with their substantiation and the methodological guidance for setting the indicators, data collection and measurement.

The methodology used for developing these indicators is in accordance with the existing regulations for the 2014-2020 programming cycle, as well as with the methodological recommendations for output and results indicators in CBC programmes.

The structure of the document follows the priorities of the programme presenting for each of them i) a summary of the respective indicators and ii) methodological details on each proposed indicators. The first part is providing the overview of the Output and Results indicators proposed for the respective priority, indicating the target and, where relevant, their baseline value. The second is presenting the definition of the indicator, the source of data, the substantiation for selecting the indicator and the proposed baseline and target values as well as indication on calculation and measurement of the indicator.

As mentioned above, the methodological guidance documents for setting indicators for the ENI CBC programmes were closely followed with most of the thematic objectives containing at least one of the recommended Common Output Indicators together with additional relevant indicators. Results indicators are also identified for each of the priorities of the programme.

# Presentation of the indicators

# Priority 1.1 – Institutional cooperation in the educational field for increasing access to education and quality of education

## Summary of indicators

| Indicator |  | Baseline | Target |
| --- | --- | --- | --- |
| COI 111 Number of institutions using programme support for cooperation in education, R&D and innovation |  | NA | 20 |
| OI 112 Number of people benefitting from all types of activities that received funding within the CBC programme |  | NA | 5000 |
| OI 113 Number of rehabilitated / modernized educational institutions |  | NA | 5 |
| RI 111 Percent of tertiary education students from eligible area from total no. of students |  | 18% | 21% |
| RI 112 Employment rate in the eligible area |  | 42.45% | 45% |
| Indicator coding system: e.g. C OI XXX, OI XXX, RI XXX |  |  |  |
| C OI – Common Output Indicator | OI – Output Indicator | RI – Result Indicator |  |
| XX – Priority Number (First two digits) | X – Indicator Number (Last digit) |  |  |

## Methodological details on proposed indicators

| Name of indicator: Number of institutions using programme support for cooperation in education, R&D and innovation (COI 111) |  |
| --- | --- |
| Definition | Number of institutions receiving support in any form from the Programme (whether the support represents state aid or not) and using it for cooperation in education, R&D and innovation Support: includes grants, financial support other than grants, non-financial support, support that does not involve direct financial transfer (such as guidance, consultancy, etc.). Venture capital is considered as financial support. Institution: any form of organisation of which R&D or education is a primary activity, i.e. activities largely coherent with the OECD Frascati Manual definition on R&D. May hence include universities or other similar research entities, higher educational institutions, public, private, or third sector R&D institutions, etc. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. Double counting is to be avoided (institution is counted once, regardless of the number of projects/ assistance measures received) Is=∑Ii, where Is – institutions supported I – institution receiving support in the framework of the programme i –individual institutions receiving support –from 1 to n Criteria taken into consideration for setting the target value of the indicator included the following: i) the estimated financial allocation for this priority and ii) the number of higher education institutions in the eligible area (reduced on the Romanian side) and iii) priority level given to education sector and education exchanges by the two national governments (reflected in national policy documents). |
| Measuring Unit | Institutions |

| Name of indicator: Number of people benefitting from all types of activities that received funding within the CBC programme (OI 112) |  |
| --- | --- |
| Definition | Number of people that benefitted from any type of activity funded within the CBC programme People: any physical person in the eligible area |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. Double counting is to be avoided (a person is counted once, regardless of the number of projects/ projects’ activities he/she was involved in). Pp=∑Pi, where Pp –people benefitting from activities in the programme P – Person taking part in activities in the framework of the programme i – indexes the number of individual persons participating –from 1 to n Setting the target for this OI was based on the nature of activities that could receive funding under this priority, as well as on the level of funding for this priority. |
| Measuring Unit | Individuals |

| Name of indicator: Number of rehabilitated / modernized educational institutions (OI 113) |  |
| --- | --- |
| Definition | Number of educational institutions that were improved/ rehabilitated using programme funding. Education institutions: any type of public or private educational institution (for primary, secondary or tertiary education) that received funding from the program to rehabilitate its facilities |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. Double counting is to be avoided (an educational institution is counted once, regardless of the number of projects/ projects’ activities financed to support its improvement/ rehabilitation). EIr=∑EIi, where EIr –educational institutions rehabilitated/modernized EI – educational institution rehabilitated/modernized with support of the programme i – indexes the number of individual educational institutions being rehabilitated/ modernized For setting the target level the total number of educational institutions in the core eligible area (2251) was taken into account, together with the estimated financial allocation and the average cost of improvement/ rehabilitation activities (ranging from 200.000 to more than 1 million euro) |
| Measuring Unit | Educational Institutions |

| Name of indicator: Percent of tertiary education students from eligible area from total number of students (RI 111) |  |
| --- | --- |
| Definition | Percentage of tertiary education students enrolled in the educational institutions based in the eligible area from total number of students of the eligible area Students: persons that are formally enrolled in primary, secondary or tertiary education programs |
| Source of data | National Institute of Statistics in Romania National Statistical Institute in Republic of Moldova |
| Indication on Measurement and substantiation for setting the baseline and target | The formula for calculating the indicator is: SRR=(TES/TS)*100, where SRR – Student retention rate TES- total of tertiary education students in the eligible area TS – Total students in the eligible area This indicator aims to capture information on the attractiveness of the university education programs available in the eligible area in relation to the overall number of registered students (primary, secondary or tertiary) from the eligible area. The baseline value, calculated for the available 2012 data, is 18%. The target value, taking into account influence of other external factors is set for 21% (increase of 3% in 2023). |
| Measuring Unit | Tertiary Students (percent) |

| Name of indicator: Employment rate in the eligible area (RI 112) |  |
| --- | --- |
| Definition | Employment rate represents the ratio between employed population and total population aged 15-64 years expressed as percentage |
| Source of data | National Institute of Statistics in Romania National Statistical Institute in Republic of Moldova |
| Indication on Measurement and substantiation for setting the baseline and target | The calculation implies using ER = ∑(Popj*Ei )/ Pop, where ER – weighted average of employment rate in the eligible area Popj – population 15 to 64 years old for each of the administrative areas where data is collected - Galati; Vaslui, Iasi, Botoșani and Republic of Moldova Ej – employment rate for each of the administrative areas where data is collected - Galati; Vaslui, Iasi, Botoșani and Republic of Moldova Pop – total population aged 15-64 in the eligible area The baseline value, calculated for the available 2012 data, is 42.45%. The target value, taking into account influence of other external factors is set for 45% (increase of around 3% in 2023). |
| Measuring Unit | Percentage |

# Priority 1.2 – Promotion and support for research and innovation

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| COI 121 Number of institutions using programme support for cooperation in R&D and support of innovation | NA | 5 |
| RI 121 Number of filed patents applications in the eligible area | 422 | 443 |

## Methodological details on proposed indicators

| Name of indicator: Number of institutions using programme support for cooperation in R&D and support of innovation (COI 121) |  |
| --- | --- |
| Definition | Number of institutions receiving support in any form from the Programme (whether the support represents state aid or not) and using it for cooperation in R&D and innovation Support: includes grants, financial support other than grants, non-financial support, support that does not involve direct financial transfer (such as guidance, consultancy, etc.). Venture capital is considered as financial support. Institution: any form of organisation of which R&D is a primary activity, i.e. activities largely coherent with the OECD Frascati Manual definition on R&D. May hence include universities or other similar research, higher educational institutions, public, private, or third sector R&D institutions, etc. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. Double counting is to be avoided (institution is counted once, regardless of the number of projects/ assistance measures received) Is=∑Ii, where Is – institutions supported I – institution receiving support in the framework of the programme i –individual institutions receiving support –from 1 to n Criteria taken into consideration for setting the target value of the indicator included the following: i) the estimated financial allocation for this priority and ii) the number of higher education institutions in the eligible area (reduced on the Romanian side) and iii) priority level given to research and development by the two national governments (reflected in national policy documents). |
| Measuring Unit | Institutions |

| Name of indicator: Number of filed patents applications in the eligible area (RI 121) |  |
| --- | --- |
| Definition | Number of patents applications registered in the eligible area |
| Source of data | National/ regional patent offices from Romania and Republic of Moldova |
| Indication on Measurement and substantiation for setting the baseline and target | PAe=∑PAi, where PAe –patents registering technologies and innovative outcomes i – indexes the number of individual patents – from 1 to n The baseline value as for the latest 2013 available data is 422 (according to the State Office for Inventions and Trademarks in Romania for the patents applications in the counties of the eligible area - and to the State Agency on Intellectual Property of the Republic of Moldova). The target value, taking into account the dynamics of this type of activities and the existing potential is set at 443 by 2023. |
| Measuring Unit | Patents applications |

# Priority 2.1 – Preservation and promotion of the cultural and historical heritage

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| COI 211 Number of institutions using programme support for promoting local culture and preserving historical heritage | NA | 10 |
| COI 212 Number of improved cultural and historical sites | NA | 5 |
| RI 211 Number of overnights stays in the eligible area | 2070257 | 2173500 |

## Methodological details on proposed indicators

| Name of indicator: Number of institutions using programme support for promoting local culture and preserving historical heritage (COI 211) |  |
| --- | --- |
| Definition | The number of institutions that use programme support for promoting local culture and preserving historical heritage. Institution: an institution is defined as any form of organisation with the primary aim of promotion of local culture and preservation of historical heritage. Can include e.g. universities (archaeology, folklore, etc.), NGOs, community development groups, third sector organisations, museums, marketing organisations focusing on preservation and development of local culture and historical heritage for tourism purposes, etc. Support: includes grants, financial support other than grants, non-financial support, support that does not involve direct financial transfer (such as guidance, consultancy, etc.). Venture capital is considered as financial support. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. CI=∑CIi, where CI – institutions promoting culture using programme support CI –institution promoting culture or preserving historical heritage using programme support i – indexes the number of institutions promoting culture that benefitted from programme support – from 1 to n Setting the target level of this indicator took into consideration the number of cultural and historical sites, as well as cultural amenities and services, the financial allocation for this priority and an estimated value regarding the number of projects that could potentially be financed considering estimated costs. Double/multiple counting of institutions is to be avoided (an institution is counted once, regardless of the number of times it receives support through the programme). |
| Measuring Unit | Institutions |

| Name of indicator: Number of improved cultural and historical sites (COI 212) |  |
| --- | --- |
| Definition | Number of improved cultural and historical sites using programme support for promoting local culture and preserving historical heritage. Valid for site improvements of e.g. buildings, landscapes, sites or structures of local, regional, or national significance, works of monumental sculpture or paintings, new acquisitions to collections or museums, etc. The improvements must be of a permanent nature. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Aggregation of data from the project reports financed under this priority. TCS=∑CSi, where TCS – total number of cultural sites improved using programme suport CS –cultural site improved following programme support i – indexes the number cultural sites improved that benefitted from programme support – from 1 to n Setting the target level of this indicator took into consideration the number of cultural and historical sites, as well as cultural amenities and services, the financial allocation for this priority and an estimated value regarding the number of projects that could potentially be financed considering estimated costs. Double/multiple counting of sites is to be avoided (site is counted once, regardless of the number of times it receives support through the programme). |
| Measuring Unit | Cultural and historical sites |

| Name of indicator: Number of overnights stays in the eligible area (RI 211) |  |
| --- | --- |
| Definition | Overnight stay represents each night that a tourist/person is registered for in a tourist accommodation facility. |
| Source of data | National Institute of Statistics in Romania. National Bureau of Statistics of the Republic of Moldova. |
| Indication on Measurement and substantiation for setting the baseline and target | The data is made available by each country’s national statistical institute/bureau, which collect data regarding touristic accommodations periodically (annually or monthly). The baseline value, calculated using the 2012 data available at the moment of the drafting of the analysis, is 2070257 overnight stays per year. The target value, taking into account influence of other external factors (other investments/programmes) is set for 2173500 overnight stays (increase of 5% in 2023). |
| Measuring Unit | Overnight stays |

# Priority 3.1 –Development of cross border transport infrastructure and ICT Infrastructure

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| COI 311 Total length of reconstructed or upgraded roads | NA | 12 |
| OI 312 Number of joint mechanisms to support improvement of cross-border infrastructure (joint planning documents including: strategies, plans, action plans; as well as multi-modal facilitation mechanisms) developed | NA | 5 |
| OI 313 Number of additional ICT based tools developed supporting cross-border cooperation | NA | 5 |
| OI 314 Number of environmentally friendly (carbon-proofed) cross-border transport initiatives developed | NA | 4 |
| RI 311 Cross border traffic volume (by rail, road) | 3684726 | 3868962 |
| RI 312 Connectivity rate in the eligible area | 42% | 60% |

## Methodological details on proposed indicators

| Name of indicator: Total length of reconstructed or upgraded roads (COI 311) |  |
| --- | --- |
| Definition | The length of roads (in KM) where the capacity or quality of the road (including safety standards) was improved. If the upgrade is significant enough for the road to qualify as new road, it will not be counted under this indicator. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. TRI=∑RIi, where TRI – total length of roads improved (in Km) using programme suport RI –Road improved (in Km) following programme support through individual project i – indexes the number of individual projects that financed particular activities targeting improvement of roads quality –from 1 to n Setting the target level of this indicator took into consideration the financial allocation for this priority and the estimated costs of reconstruction and upgrade activities according to national standards of costs. |
| Measuring Unit | Kilometres |

| Name of indicator: Number of joint mechanisms to support improvement of cross-border infrastructure (joint planning documents including: strategies, plans, action plans; as well as multi-modal facilitation mechanisms) developed (OI 312) |  |
| --- | --- |
| Definition | Number of joint mechanisms to support improvement of cross-border infrastructure developed in the framework of the CBC programme “Joint mechanisms” include different planning documents prepared jointly and addressing cross-border infrastructure (e.g., strategies, plans, action plans etc) as well as multi-modal transport facilities |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration previous initiative of cooperation and joint interventions of the Moldovan and Romanian authorities in the eligible area. |
| Measuring Unit | Mechanisms (e.g. Strategies, Plans, Multi-modal facilities) |

| Name of indicator: Number of additional ICT based tools developed supporting cross-border cooperation (OI 313) |  |
| --- | --- |
| Definition | The number of newly developed ICT-based tools supporting overall cross border cooperation and specific processes - communications, gathering, storing and processing of data/ information etc - using programme support |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. TICT=∑Ti, where TICT– tools for ICT using programme support T –Tools developed i – indexes the number of individual ICT tools developed with the support of the programme –from 1 to n |
| Measuring Unit | ICT tools |

| Name of indicator: Number of environmentally friendly (carbon-proofed) cross-border transport initiatives developed (OI 314) |  |
| --- | --- |
| Definition | The number of initiatives aiming to improve cross-border transport with low environmental impact resulted from the promotion and implementation of carbon proofed technologies and innovative solutions developed in the framework of the CBC programme |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. TIef=∑Ii, where TIef – Total number of initiatives with low environmental impact I – individual initiative developed i – indexes the number of individual initiatives with low environmental impact –from 1 to n |
| Measuring Unit | Initiatives |

| Name of indicator: Cross border traffic volume (by rail and road) (RI 311) |  |
| --- | --- |
| Definition | Cross-border traffic is defined as number of individual crossings through the Romania – Republic of Moldova border crossing points, regardless of the direction of the traffic. |
| Source of data | Border Police of Romania / Border Police of Republic of Moldova. |
| Indication on Measurement and substantiation for setting the baseline and target | The data is made available through request by either the Romanian or Moldovan border police. Since counts of border crossings imply that one crossing is registered by both of the countries’ crossing points (i.e. the values should coincide), the data from only one institution should be sufficient for the assessment. TV=TVrd +TVra where TV –cross border traffic volume; TVrd – yearly traffic volume by road TVra –yearly traffic volume by rail The baseline value, was calculated by adding the number of road and rail crossings registered by the Romanian Border Police for the year 2013. The target value takes into consideration the influence of other external factors as the political and economic contexts, and was estimated to reach a 5 % increase in 2023. |
| Measuring Unit | Crossings on cross points (auto and rail) |

| Name of indicator: Connectivity rate in the eligible area (RI 312) |  |
| --- | --- |
| Definition | The percentage of households that are connected to broadband or high speed internet from the total number of households in the core eligible area. |
| Source of data | National Institute of Statistics in Romania. National Bureau of Statistics of the Republic of Moldova. |
| Indication on Measurement and substantiation for setting the baseline and target | The data is made available by each country’s national statistical institute/bureau which collects data regarding internet connectivity at national and local levels. The following formula is recommended for the indicator: HC = ∑Hi*rj, where HC - percentage of households connected to broadband or high speed internet from the total number of households in the core eligible area Hi – percentage of households connected to broadband relative to the respective region where data is collected - (a) Galati; b) Vaslui, Iasi, Botoșani and c) Republic of Moldova) rj - multiplication factor based on the share of population of the three regions in the total eligible area The baseline value was set using the percentage of households connected to the internet at regional level for Romania (one value for Galati as part of SE Region and one cumulated value for Iasi, Botoșani and Vaslui, as part of the NE Region) and national level for Republic of Moldova. The final weighted average for percentage of households connected to the internet was calculated multiplying each of these three values with the share of population from total population of the eligible area. The target value of 60% was determined by taking into account the influence of other external factors (other public or private investments in communication backbone development) as well as OI 212 described above, and the increased role of communications for economic development, making its development a high level priority in terms of time. |
| Measuring Unit | Percentage (units connected out of total number of units) |

# Priority 4.1 - Support to the development of health services and access to health

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| COI 411 Population covered by improved health services as a direct consequence of programme support | NA | 200000 |
| OI 412 Number of medical service infrastructure units improved | NA | 3 |
| RI 412 Number of newly registered cases of illness | 2780 | 2502 |

## Methodological details on proposed indicators

| Name of indicator: Population covered by improved health services as a direct consequence of programme support (COI 411) |  |
| --- | --- |
| Definition | The population of a certain area expected to benefit from the health services improved through support from projects within the programme. Support: includes new or improved buildings, new equipment for various type of health service (prevention, outpatient or inpatient care, aftercare), or new or improved health service structures (e.g. telemedicine). The indicator excludes multiple counting at the project level even if the intervention includes several services targeting the same persons: one person still counts as one even if that person will benefit from improvement of several different services which were supported by the project. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration the number (hospitals / clinics / etc.) and concentration of health units across the core eligible area and the general size of the urban and rural settlements across the core eligible area. |
| Measuring Unit | Inhabitants |

| Name of indicator: Number of medical service infrastructure units improved (OI 412) |  |
| --- | --- |
| Definition | The number of medical service units that are improved/ rehabilitated through programme support. Medical service unit: Includes all buildings and utilities of any health services institution whose use is directly linked to the provision of health services (e.g. ambulatory centres/ laboratories / etc.). |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration the number of medical institutions (hospitals / clinics / etc.) across the core eligible area and estimated costs of such projects ranging from €150000 to €1500000 referenced to the total financial allocation for this priority. The measuring of the indicator will avoid double/multiple counting. One medical unit will be counted only once, even if its rehabilitation is the result of multiple projects. |
| Measuring Unit | Medical infrastructure units |

| Name of indicator: Number of newly registered cases of illness (RI 411) |  |
| --- | --- |
| Definition | The number of new cases of illnesses registered by physicians at the core eligible area. The indicator takes into account only newly discovered illnesses that were not registered before. |
| Source of data | National Institute of Statistics in Romania. National Bureau of Statistics of the Republic of Moldova. |
| Indication on Measurement and substantiation for setting the baseline and target | The data is made available by each country’s national statistical institute/bureau which collect data on the health system at territorial level. NI=∑NIi*rj, where NI – new cases of illness i – indexes the national average for the country (Romania or Republic of Moldova) rj – multiplication factor for each country, based on the share of population The baseline value of 2780 thousands was set by using the 2013 data available at the time of the drafting of the territorial analysis. In the case of Romania, the national value was used in the calculation, which was correlated with the percent value of the population of the Romanian counties in the core eligible area out of the total population of Romania. In the case of Republic of Moldova the national value was used. The target value of 2502 thousands (decrease of approximately 10%) was determined by taking into account the improvements brought on by the future development of the health system at the core eligible area level using public and private funding, as well as the improvements measured through COI 411 and OI 412 described above. |
| Measuring Unit | Cases of illness (thousands) |

# Priority 4.2 – Support to joint activities for the prevention of natural and man-made disasters as well as joint action during emergency situations

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| COI 421 Population benefiting from flood protection measures | NA | 10000 |
| OI 422 Number of joint actions, including soft operations, as well as joint infrastructure investments in the field of emergency situations and the prevention of manmade disasters. | NA | 20 |
| RI 421 Average response time for emergency situations in the eligible area | 15’06’’ in 2014 | 14’03’’’ in 2023 |

## Methodological details on proposed indicators

| Name of indicator: Population benefiting from flood protection measures (COI 421) |  |
| --- | --- |
| Definition | Number of people exposed to flood risk where vulnerability decreased as a direct consequence of a supported project. The indicator excludes multiple counting at the project level even if the intervention includes several services targeting the same persons: one person still counts as one even if that person will benefit from various flood protection measures. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration the areas in risk of flooding and the respective inhabitants. |
| Measuring Unit | Persons |

| Name of indicator: Number of joint actions, including soft operations as well as joint infrastructure investments in the field of emergency situations and the prevention of man-made disasters (OI 422) |  |
| --- | --- |
| Definition | Number of joint actions in the field of emergency situations and the prevention of manmade disasters developed in the framework of the CBC programme Joint actions – actions involving partners from both countries of the eligible area consisting of - soft operations such as exchange experience; trainings; study visits; common planning sessions; newly developed: maps, data bases, systems/structures, equipments and - infrastructure investments |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration previous initiative of cooperation and joint interventions of the Moldovan and Romanian authorities in the eligible area. |
| Measuring Unit | Joint actions |

| Name of indicator: Average response time for emergency situations in the eligible area (RI 421) |  |
| --- | --- |
| Definition | Represents the average response time to emergency situations in the eligible area. |
| Source of data | Information provided by the General Inspectorate for Emergency Situations of Romania and Civil Protection and Exceptional Situations Service in Republic of Moldova |
| Indication on Measurement and substantiation for setting the baseline and target | The data for Romanian counties within the eligible area, as communicated by the General Inspectorate for Emergency Situations sets an average value of 15´30” for all types of emergency situations calculated as an average between rural and urban intervention times. The data for Republic of Moldova registers an average response time of 6 minutes for urban localities and 21 minutes for rural ones. The weighted average of the two response times taking into account the share of population in urban and rural localities (42% in urban and 58 in rural area) reflects an overall average response time of 14’42’’. The overall baseline value of the indicator using arithmetical average of the 2 values registered in Romania and Republic of Moldova is 15’06’’. The target value takes into consideration the influence of other external factors, as well as the target set by the Romanian General Inspectorate for Emergency Situations of 13´50” as well as a decrease of 3% for Republic of Moldova is proposed to reach 14’03’’. |
| Measuring Unit | Minutes |

# Priority 4.3 Prevention and fight against organized crime and police cooperation

## Summary of indicators

| Indicator | Baseline | Target |
| --- | --- | --- |
| OI 431 Number of participants involved in joint capacity building activities (exchanges of experience, study visits, trainings, etc.) | NA | 300 |
| OI 432 Number of modernized facilities of police, border police and custom services from the eligible area | NA | 10 |
| RI 431 Increase of the ratio of annual number of persons crossing the border to the number of customs personnel directly employed at the border crossing points | 6639 | 7635 |
| RI 432 Level of trust and confidence of citizens in the police. | Romania 47.1% Republic of Moldova 29 % | 5% increase in 2023 |

## Methodological details on proposed indicators

| Name of indicator: Number of participants involved in joint capacity building activities (exchanges of experience, study visits, trainings, etc.) (OI 431) |  |
| --- | --- |
| Definition | Number of participants that will participate in knowledge and experience exchange activities organized using programme support. |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration previous initiative of cooperation and joint interventions of the Moldovan and Romanian authorities in the eligible area and the financial allocation of for this priority, as well as the extent to which the programme can implement these activities at the core eligible area level. |
| Measuring Unit | Persons |

| Name of indicator: Number of modernized facilities of police, border police and custom services from the eligible area (OI 432) |  |
| --- | --- |
| Definition | Number of police, police border and customs services modernized using support of the programme |
| Source of data | Database of projects/ Projects’ reports |
| Indication on Measurement and substantiation for setting the target | Measurement will use aggregation of data from the project reports financed under this priority. Setting the target level of this indicator took into consideration the existing police border and customs service facilities as well as the estimated financial allocation for this priority. |
| Measuring Unit | Facilities |

| Name of indicator: Increase of the ratio of annual number of persons crossing the border to the number of customs personnel directly employed at the border crossing points (RI 431) |  |
| --- | --- |
| Definition | The increase in the number of registered number of persons crossing the border per customs officer (person directly employed at the border crossing point) |
| Source of data | National Agency for Fiscal Administration, Ministry of Interior of Romania / Customs Office and Border Police of the Republic of Moldova. |
| Indication on Measurement and substantiation for setting the baseline and target | The data should be made available upon request from the two ministries of interior. If not already, systems and mechanisms should be put in place to capture this data automatically. ITBE= TV / CE, where ITBE – number of number of persons crossing the border per customs employee per year; TV – Cross-border crossings per year (Cross-border traffic volume) CE – Number of customs employees in the eligible area. The baseline value is 6639 (number of crossings/ number of customs employees) The target value takes into consideration the influence of other external factors, as the political and economic context, and was estimated to reach 15% increase in 2023 (a ratio of 7635). |
| Measuring Unit | Increase of ratio (percentage) |

| Name of indicator: Level of trust of citizens in the police (RI 432) |  |
| --- | --- |
| Definition | Represents the level of trust of the eligible area's population in the local police and its services. |
| Source of data | Annual Opinion barometers INSCOP for Romania and IPP for Republic of Moldova |
| Indication on Measurement and substantiation for setting the baseline and target | The two surveys are carried out on annual basis by these independent research institutes. The results for Romania are expressed as national average level of trust and this value would be used for the eligible area. The overall value for level of trust in police is calculated using arithmetical average of the values of the two countries. The baseline value is 38.05%. It was calculated using the Romanian national average level of trust in police for 2015 (47,1%) and the national average of level of trust in police in Republic of Moldova (29%). From the methodological point of view, the percentages represent the cumulated population with a positive trust level. The target value takes into consideration the influence of other external factors, as the political and economic context, and was estimated to a 5% increase in 2023, reaching 43%. |
| Measuring Unit | Percentage |

# ANNEX V. REPORT ON STRATEGIC ENVIRONMENTAL ASSESSMENT

Annex 5 can be consulted in attachment.

The programme will operate a manual transfer of data from the information system of the programme to KEEP in the first years of implementation. The possibilities for a shift to automatic transfer in xml format to KEEP will be considered.

The KEEP database is also used by the EC for the collection and representation of basic information on programmes such as the numbers of projects and partners per programme and countries.

Commission Implementing Regulation (EU) No 897/2014 of 18 August 2014 laying down specific provisions for the implementation of cross-border cooperation programmes financed under Regulation (EU) No 232/2014 of the European Parliament and the Council establishing a European Neighbourhood Instrument

These include the Financial Regulation, the Financial Regulation Rules of Application, ENI regulation, ENI CBC Implementing Regulation, ENI CBC Programming Document, Communication and Visibility Manual for EU External Actions

The EC implementing regulation (EU) no897/2014, Suggestions for the Common Output Indicators for ENI CBIC 2014-2020 (Interact), Guidance for developing results indicators in ENI CBC programmes (Interact)

In accordance with the regulation for programming, baseline values are to be set for result indicators only

The same acronyms are used throughout this document

In accordance with the available data of the Romanian and Moldovan statistical institutes

Documented through independent assessment of various schools rehabilitation projects (ROP database on implemented projects and web-pages of RDAs and individual local authorities)

As defined by the Romanian National Statistics Institute

This indicator is part of the larger COI 111, but would be monitored separately to highlight the support for R&D

OECD (2002),Frascati Manual 2002: Proposed Standard Practice for Surveys on Research and Experimental Development, The Measurement of Scientific and Technological Activities, OECD Publishing.

The increase in the overnight stays reflects the increase of attractiveness of the cultural and historical sites in the area (making use of the touristic potential of the area).

The data on the internet connectivity was available at regional level, hence it was extrapolated to the particular counties of that region.

51.2 for Galati, 45.7 for Iasi, Vaslui and Botoșani and 38.95 for Republic of Moldova

0.09 for Galati, 0.28 for Iasi, Vaslui and Botoșani (cumulated) and 0.63 for Republic of Moldova

The indicator only counts the newly registered diseases, as reported by the medical staff of each country.

Including but not limiting to exchange experience; trainings; study visits; common planning sessions; newly developed: maps, data bases, systems/structures, equipment, etc.

Representing an aggregation of the average response time to various emergency situations (e.g., fire, floods, emergency medical interventions, SMURD etc.) as calculated and communicated on annual basis by the General Inspectorate for Emergency Situations in Romania and Civil Protection and Exceptional Situations Service in Republic of Moldova

As per the 2014 reported population of 1502996 in urban localities and 2054638 in rural ones

Considering the differentiated type of data provided by the customs services, for Romania the number of available posts was counted, while in the case of Republic of Moldova the number of customs collaborators.